## Timeline
| 2004 | 2005 | 2006
Spring Semester
Pilot Group(s) | 1: Application process | 1: Second semester of pilot
| 1: Finalize participant roster by _____ | 1: Mentor group 2
2: First semester of pilot
Curriculum Development | Find curriculum developer | CR visits classes, writes curricula
Begin working with them
Evaluation | Finalize training objectives | February: teacher and student focus groups
| Develop pre- and post- questionnaires | April: mid-course review #2 **
June: teacher and student focus groups
June: pilot #1 post- surveys
Distribution |  |  | launch!
Summer
Pilot Group(s) | 1: Training conference*
1: Receive digital cameras
Curriculum Developer
Evaluation | pilot #1 pre- surveys | Meeting to assess eval process
Distribution |  | Create "best of TQ pilot" commentary collection | Launch conference (at CAJE?)
Workshops, presentations at CAJE
Fall Semester
Pilot Group(s) | 1: First semester of pilot | 1: Mentor group 2?
| 2: Application process | 2: Second semester of pilot
2: Finalize participant roster by _____
Curriculum Development | CR visits classes, writes curricula | Visits classes, writes curricula
Evaluation | November: mid-course review #1** | October: mid-course review #3 **
December: pilot #2 post- surveys
Winter Break
Pilot Group(s) | 2: Training conference*
2: Receive digital cameras
Evaluation | Meeting to assess eval process | Final meeting?
pilot #2 pre- surveys
Notes
* Training Conference includes training in the importance of evaluation and what they need to do according to our evaluation procedures
** Mid-course review: We look at the data from Snapshot visits, teacher reflective essays, and other sources and

## Job Descriptions
Shai | Ilana | External Evaluator
role: different set of eyes
teaching, training | manage communications w/ teachers | question our interpretations
| administer recruitment process | read/look at eval data
consultations with pilot teachers |  | meet with us to brainstorm, review
consultations with other teachers |  | keep us on task w/ the eval plan
limited number of site visits
Snapshot evaluations of classes
networking
fundraising
marketing
supervision
Internal Evaluation: measure, interpret, make recommendations
Teachers | Ed Directors | Curric. Developer
Learn TorahQuest methods | Snapshot evaluations of classes | Classroom visitations
Lead TorahQuest sessions | report on impact within school env. | Curriculum writing
Write reflective essays
Participate in focus groups
visit each other's classrooms?
Siegal
teach educational, biological basis of TorahQuest
teach history of Jewish response?
train teachers to reflect on experiences